## Cover
PRODUCT LAUNCH MASTER CHECKLIST
Amazon Working Backwards · AWS Product Strategy · MVP Framework · Gartner · Product School
David W. Lucky ¦ Senior Product Marketing Leader & Principal ¦ CloudScale Advisory ¦ cloudscaleadvisory.com
PRODUCT LAUNCH MASTER CHECKLIST
Amazon Working Backwards · AWS Product Strategy · MVP Framework · Gartner · Product School
Product / Project Name: | [Insert Product Name]
Launch Date (Target): | [Insert Date]
Launch Type: | [ ] MVP Launch [ ] Full Product Launch
Launch Owner: | [Insert Name]
Version: | v2.0
METHODOLOGY SOURCES
Framework | Where It Appears in This Checklist
Amazon Working Backwards | Phase 0 — PR/FAQ process, customer-first thinking, problem validation (workingbackwards.com)
AWS Prescriptive Guidance | Phase 0 — Vision statement, OKRs, user personas, customer journey, business case, feature prioritization
MVP Development Framework | Phase 0 — Launch type decision, feature scoping, feedback loop design, MVP success criteria
Gartner Product Launch | Phases 1–4 — Channel strategy, pricing, legal sign-off, partner briefing, sales enablement
Product School | Phases 2 & 5 — Systems/QA gates, platform-specific release checks, decision framework
CHECKLIST PHASES
Phase | Tab Name | Key Focus
Phase 0 | Working Backwards | PR/FAQ, AWS vision, MVP decision gate — MUST complete before Phase 1
Phase 1 | Pre-Launch Planning | Positioning, pricing, legal, partner plan — all traced to Phase 0 PR/FAQ
Phase 2 | Systems & Operations | QA, infrastructure, compliance, analytics tied to Phase 0 KRs
Phase 3 | GTM Execution | Content, PR, ads, events — all derived from Phase 0 PR/FAQ language
Phase 4 | Sales & Support | Enablement, FAQs, onboarding — grounded in PR/FAQ customer story
Phase 5 | Launch Day | Gate checks, execution, feedback collection (MVP)
Phase 6 | Post-Launch | KR tracking, PR/FAQ accuracy review, next iteration

## 0-Working Backwards
PHASE 0 ¦ Working Backwards — Amazon PR/FAQ & Product Vision
Category | Task | Description / Guidance | Due Date | Status | Owner | Reference / Link | Signature
AMAZON WORKING BACKWARDS — PR/FAQ
PR/FAQ | Write the press release first | Draft the external press release BEFORE any GTM planning. Include: Heading (product name), Subheading (target customer + benefit), Summary paragraph with proposed launch date, Problem paragraph (customer POV, TAM quantified), Solution paragraph(s) with competitive differentiation, two quotes (company + hypothetical customer), and call-to-action. |  | ○ Not Started |  | GATE ITEM — nothing in Phase 1 locks until PR/FAQ approved. Ref: workingbackwards.com
PR/FAQ | External FAQ completed | Answer all questions a customer or journalist would ask: How does it work? What does it cost? How do I get started? What is the return/cancellation policy? Write in plain language, no corporate jargon. |  | ○ Not Started
PR/FAQ | Internal FAQ completed | Anticipate hard questions from every internal stakeholder: Finance (P&L impact, pricing model), Legal (compliance, IP), Ops (fulfillment, support scale), Engineering (technical feasibility, timeline), HR (headcount needs). Include realistic risk assessment — not rose-colored glasses. |  | ○ Not Started |  | Cover finance, legal, ops, engineering, HR
PR/FAQ | PR/FAQ reviewed & iterated | Share the PR/FAQ draft with senior stakeholders for written feedback. Iterate until the customer problem and solution are so clear that any reader immediately understands the value. Typically requires 3–5 revision cycles. |  | ○ Not Started |  | Expect 3–5 revision cycles before lock
PR/FAQ | PR/FAQ approved — launch gate cleared | Final sign-off from executive sponsor and product lead. This approval is the formal gate to proceed into Phase 1 planning. No GTM budgets, timelines, or team assignments are finalized before this point. |  | ○ Not Started |  | GATE ITEM — executive sign-off required ✍
AWS PRODUCT STRATEGY — START WITH WHY
Vision | Product vision statement (OKR framework) | Articulate the long-term business objectives (O) and the shorter-term key results (KR) that signal the product is on track. The vision statement is the anchor that keeps all teams aligned as the product evolves through development. |  | ○ Not Started |  | Ref: AWS Prescriptive Guidance — Start with Why
Vision | User personas defined | Identify target user groups. For each persona, document: who they are, how they behave, why they will use the product, and what success looks like for them. Determine if any user segments require expensive features that dilute the business case. |  | ○ Not Started
Vision | Customer journey maps completed | Map the as-is journey (current frustrations, friction points) and the target journey (how the product resolves them). Include systems and technical capabilities needed to bridge the gap. Validate with real customer input. |  | ○ Not Started |  | Ref: Design thinking / customer empathy
Vision | Success metrics defined (3+ measurable KRs) | Define at least three quantifiable success metrics directly linked to business outcomes — not just product activity metrics. Set initial targets with a 3–5 year time horizon. Identify how each metric will be measured and reported. |  | ○ Not Started |  | Ref: AWS — Define Success Metrics stage
Business Case | Business case developed | Build the business case using the success metrics as primary value drivers. Include revenue upside, cost savings, and efficiency gains. Estimate development and operational costs using the product vision as the cost basis. Challenge assumptions with data. |  | ○ Not Started |  | Delay business case until vision + metrics are locked
MVP DECISION GATE
MVP | Define launch type: MVP vs. full product | Explicitly decide whether this launch is a Minimum Viable Product (core features only, feedback-first) or a full product launch. This decision shapes the scope of every downstream phase. MVP launches prioritize speed, feedback collection, and iteration over completeness. |  | ○ Not Started |  | MVP = core features + feedback loop. Full = complete GTM motion
MVP | Feature backlog prioritized by value | Prioritize features using the value drivers from the business case. For MVP: identify the single core problem to solve and ruthlessly descope everything else. For full launch: sequence features by customer impact and technical dependency. |  | ○ Not Started |  | Ref: AWS — Prioritize Features & Plan Delivery
MVP | MVP success criteria defined | For MVP launches: define what 'validated' looks like. How many users? What behavior signals? What feedback threshold triggers a go/no-go for full product investment? Document these criteria before launch. |  | ○ Not Started
MVP | Product discovery & market research complete | Validate that the product solves a genuine user problem. Review competitor landscape, user pain points, market size. Confirm the problem is worth solving at the scale required for business case viability. |  | ○ Not Started |  | Ref: MVP Development Guide — Product Discovery
David W. Lucky ¦ Senior Product Marketing Leader & Principal, CloudScale Advisory ¦ cloudscaleadvisory.com
cloudscaleadvisory.com · Strategic GTM for Cloud & AI

## 1-Pre-Launch Planning
PHASE 1 ¦ Pre-Launch Strategy & Planning
Category | Task | Description / Guidance | Due Date | Status | Owner | Reference / Link | Signature
DECISION-MAKING FRAMEWORK
Decision Framework | Define decision scope & decision-maker | Clarify: what is being decided, by when, who the decision-maker is, who provides input, and who is affected. Document in a Decision Log. Link to approved PR/FAQ as the source of truth for all decisions. |  | ○ Not Started |  | All decisions must align with approved PR/FAQ
Decision Framework | Commit & communicate final decision | Record the final decision, rationale, communication method, and earliest date to revisit. |  | ○ Not Started
PRODUCT DEFINITION & POSITIONING
Product | Feature definition & USPs — aligned to PR/FAQ | Define product functionality and USPs. Must be directly traceable to the solution paragraph in the approved PR/FAQ. Any feature not in the PR/FAQ requires a PR/FAQ revision before proceeding. |  | ○ Not Started |  | GATE: must align with approved PR/FAQ
Product | Positioning statement approved | Positioning must reflect the problem and solution language from the PR/FAQ. Target audience, key benefit, and competitive differentiation must be consistent across both documents. |  | ○ Not Started |  | GATE ITEM ✍
Product | Messaging house completed | Build messaging hierarchy: headline, pillars, proof points. All messaging derives from the PR/FAQ customer language — not internal jargon. |  | ○ Not Started
Product | JTBD customer interviews validated | Conduct Jobs-To-Be-Done interviews to validate that the PR/FAQ problem paragraph reflects real customer language and actual purchase triggers. |  | ○ Not Started |  | Use JTBD interview script
COMMERCIAL READINESS
Commercial | Finalize pricing & packaging | Triangulate cost, competitive pricing, and customer value. Pricing must be consistent with the PR/FAQ's description of how customers get started. Validate billing system supports the model. |  | ○ Not Started |  | GATE ITEM ✍
Commercial | Channel strategy confirmed | Assess direct vs. indirect mix. Confirm channel partners have skills to sell the product as described in the PR/FAQ. |  | ○ Not Started
Commercial | Contract templates & legal sign-off | Create or update warranties, contract templates, licensing agreements. Legal must sign off before launch. |  | ○ Not Started |  | GATE ITEM ✍
Commercial | Ordering & billing validation | Confirm billing and ordering systems are configured and tested. |  | ○ Not Started
PARTNER & STAKEHOLDER BRIEFING
Partners | Partner briefing plan | Brief partners using PR/FAQ language. Partners should be able to articulate the customer problem and solution in the same terms as the press release. |  | ○ Not Started
Partners | Analyst briefing scheduled | Schedule briefings with key analysts. Share PR/FAQ summary as the briefing foundation. |  | ○ Not Started
David W. Lucky ¦ Senior Product Marketing Leader & Principal, CloudScale Advisory ¦ cloudscaleadvisory.com
cloudscaleadvisory.com · Strategic GTM for Cloud & AI

## 2-Systems & Ops
PHASE 2 ¦ Systems & Operations Readiness
Category | Task | Description / Guidance | Due Date | Status | Owner | Reference / Link | Signature
PRODUCT ENGINEERING & QA
Engineering | Feature completeness & code freeze | Confirm all launch-scope features (as defined in prioritized backlog from Phase 0) are complete. For MVP: confirm only core features are in scope. Code freeze date set. |  | ○ Not Started |  | GATE ITEM ✍
QA | End-to-end QA testing signed off | Test all product flows. For MVP: focus testing on the core user journey defined in the PR/FAQ. Zero launch-blocking bugs. |  | ○ Not Started |  | GATE ITEM ✍
QA | Performance & stress testing complete | Validate system handles expected launch traffic. For MVP: define minimum viable performance threshold. |  | ○ Not Started
UX/UI | UX/UI review approved | Final review against the 'easy to get started' promise in the PR/FAQ. The onboarding experience must match what was described. |  | ○ Not Started
SYSTEMS & INFRASTRUCTURE
Systems | Infrastructure readiness confirmed | Hardware, software, servers, network capacity confirmed. Stress tests run. Scaling plan documented. |  | ○ Not Started |  | GATE ITEM ✍
Systems | Billing & pricing system validated | Billing system handles the pricing model described in PR/FAQ. Invoicing, payment, subscription management tested. |  | ○ Not Started
Systems | CRM / Sales system configured | CRM updated with new product. Lead routing, deal stages, and opportunity tracking configured. |  | ○ Not Started
Data | Analytics & dashboards live | Success metrics from Phase 0 are instrumented. Dashboards configured to track KRs defined in vision statement. |  | ○ Not Started |  | Must track KRs from Phase 0 vision
Systems | Rollback plan documented & tested | Rollback procedure defined, documented, and tested. Especially critical for MVP launches where rapid iteration is expected. |  | ○ Not Started
Legal | Security & compliance sign-off | Security review complete. Data privacy (GDPR/CCPA) confirmed. Regulatory requirements from internal FAQ addressed. |  | ○ Not Started |  | GATE ITEM ✍
David W. Lucky ¦ Senior Product Marketing Leader & Principal, CloudScale Advisory ¦ cloudscaleadvisory.com
cloudscaleadvisory.com · Strategic GTM for Cloud & AI

## 3-GTM Execution
PHASE 3 ¦ Go-To-Market Execution
Category | Task | Description / Guidance | Due Date | Status | Owner | Reference / Link | Signature
LAUNCH PLANNING
Planning | Launch objectives aligned to Phase 0 success metrics | GTM objectives must be direct descendants of the success metrics defined in Phase 0. No new objectives introduced at this stage without a PR/FAQ revision. |  | ○ Not Started |  | GATE: trace to Phase 0 KRs
Planning | Master launch timeline approved | For MVP: compressed timeline focused on getting to user feedback as quickly as possible. For full launch: comprehensive calendar across all functions. |  | ○ Not Started
Planning | Launch budget approved | For MVP: lean budget prioritizing user acquisition and feedback infrastructure. For full launch: complete by department and quarter. |  | ○ Not Started
Planning | Risk register & contingency plan | Address risks surfaced in the internal FAQ from Phase 0. These are the 'dragons to slay' — they should already be known. |  | ○ Not Started |  | Ref: Internal FAQ risk items from Phase 0
CONTENT & COMMUNICATIONS
Content | Content strategy built from PR/FAQ language | All content (blog, social, ads, email) derives from the press release language. The headline of the press release should be recognizable across all content touchpoints. |  | ○ Not Started |  | PR/FAQ is the content brief
Content | Website & landing pages live | Product pages reflect PR/FAQ messaging. The 'get started' CTA matches the onboarding path described in the press release. |  | ○ Not Started |  | GATE ITEM ✍
Content | External PR/FAQ adapted for website FAQ | The external FAQ from Phase 0 is adapted and published as the customer-facing FAQ. This was already written — adapt don't rewrite. |  | ○ Not Started |  | Derived from Phase 0 External FAQ
Content | Sales enablement materials ready | Pitch decks, battle cards, and one-pagers all use PR/FAQ language. Sales team can answer the same questions as the press release. |  | ○ Not Started
PR | Press release finalized for distribution | The Phase 0 PR/FAQ press release is production-ready: fact-checked, legal-approved, embargoed if needed. This is the document written in Phase 0 — polish, don't restart. |  | ○ Not Started |  | Derived from Phase 0 PR draft
PR | Media & influencer outreach plan | Target media list built. Embargo schedule set. Influencer seeding plan aligned to launch date. |  | ○ Not Started
Advertising | Advertising plan approved | Paid media plan defined. For MVP: minimal spend, focus on target segment. For full launch: complete multi-channel plan. |  | ○ Not Started
Events | Launch event / webinar planned | Event agenda built around the PR/FAQ narrative — customer problem, solution demo, differentiation. |  | ○ Not Started
CHANNEL & DISTRIBUTION
Channel | Distribution channels ready | All channels confirmed, contracted, and trained to sell the product as described in the PR/FAQ. |  | ○ Not Started
Channel | Marketing KPI tracking live | KPIs trace to Phase 0 success metrics. UTM parameters, conversion tracking, and CRM integration confirmed. |  | ○ Not Started |  | GATE: must link to Phase 0 KRs
David W. Lucky ¦ Senior Product Marketing Leader & Principal, CloudScale Advisory ¦ cloudscaleadvisory.com
cloudscaleadvisory.com · Strategic GTM for Cloud & AI

## 4-Sales & Support
PHASE 4 ¦ Sales & Customer Support Prep
Category | Task | Description / Guidance | Due Date | Status | Owner | Reference / Link | Signature
SALES READINESS
Sales | Sales strategy & playbook finalized | Sales playbook is grounded in the PR/FAQ: the customer problem is the qualifying question, the solution is the demo narrative, and the competitive differentiation is the objection-handling guide. |  | ○ Not Started |  | PR/FAQ = the sales story
Sales | Sales team training completed | Train reps to tell the same story as the press release. If a customer reads the PR and then talks to sales, the message must be identical. |  | ○ Not Started |  | GATE ITEM ✍
Sales | Internal & external FAQs distributed | Internal FAQ from Phase 0 is the sales team's objection-handling bible. External FAQ is the customer-facing resource. |  | ○ Not Started |  | Derived from Phase 0 FAQs
Sales | Sales enablement materials complete | All materials (decks, one-pagers, demo scripts) reviewed against PR/FAQ for message consistency. |  | ○ Not Started
CUSTOMER SUPPORT READINESS
Support | Support model & SLAs defined | Support tiers, SLAs, and escalation paths defined. For MVP: lightweight model focused on capturing feedback, not just resolving issues. |  | ○ Not Started
Support | Customer service team trained | Support staff trained on product using same language as external FAQ. Common questions already answered in the FAQ. |  | ○ Not Started
Support | Customer onboarding plan ready | Onboarding reflects the 'how to get started' section of the press release. The first customer experience must match what was promised. |  | ○ Not Started
Support | Customer success & feedback loop defined | For MVP: define exactly how user feedback is collected, who reviews it, and how it feeds back into the feature backlog. Feedback loop is a first-class launch deliverable. |  | ○ Not Started |  | Critical for MVP launches
INTERNAL ALIGNMENT
Alignment | Internal launch briefing sent | All teams briefed using the PR/FAQ as the anchor document. Every internal stakeholder should be able to answer: what problem does this solve, for whom, and how is it different? |  | ○ Not Started |  | GATE ITEM ✍
Alignment | Stakeholder communication plan active | Weekly status updates to leadership through launch. Format: readiness score, gate item status, top 3 risks. |  | ○ Not Started
David W. Lucky ¦ Senior Product Marketing Leader & Principal, CloudScale Advisory ¦ cloudscaleadvisory.com
cloudscaleadvisory.com · Strategic GTM for Cloud & AI

## 5-Launch Day
PHASE 5 ¦ Launch Day — Release Checklist
Category | Task | Description / Guidance | Due Date | Status | Owner | Reference / Link | Signature
FINAL GATE CHECK (T-24HRS)
Gate | Final QA & code freeze confirmed | Zero launch-blocking bugs. QA lead signs off. |  | ○ Not Started |  | GATE ITEM ✍
Gate | Security & compliance final | Legal/security final sign-off confirmed. |  | ○ Not Started |  | GATE ITEM ✍
Gate | PR/FAQ message consistency final check | Spot-check: website headline, press release, sales deck, and support FAQ all tell the same story as the approved PR/FAQ. |  | ○ Not Started |  | Last message consistency gate
Gate | Support & ops on standby | All teams briefed. On-call rotation active. Escalation path confirmed. |  | ○ Not Started
Gate | Team alignment briefing complete | Final all-hands: launch time, roles, monitoring, escalation. |  | ○ Not Started
LAUNCH DAY EXECUTION
Launch | Product available across all channels | Live on all distribution channels. Verify with a real test transaction or download. |  | ○ Not Started |  | GATE ITEM ✍
Launch | Website & content published | All pages live. PR/FAQ-derived FAQ published. CTA links working. |  | ○ Not Started
Launch | Press release distributed | Wire distribution sent. Direct journalist outreach executed. Embargo lifted. |  | ○ Not Started
Launch | Social & email campaigns activated | Social posts published. Launch email sent. Open rate monitoring active. |  | ○ Not Started
Launch | Launch event / webinar executed | Event running on schedule. Demo, speakers, recording confirmed. |  | ○ Not Started
Launch | Monitoring & analytics confirmed live | All tracking firing: web analytics, conversion pixels, CRM capture, infra monitoring. |  | ○ Not Started
MVP | Feedback collection mechanisms active | For MVP launches: in-app feedback, NPS prompt, user session recording, and support ticket tagging all live from Day 1. |  | ○ Not Started |  | MVP gate: feedback loop must be live at launch
David W. Lucky ¦ Senior Product Marketing Leader & Principal, CloudScale Advisory ¦ cloudscaleadvisory.com
cloudscaleadvisory.com · Strategic GTM for Cloud & AI

## 6-Post-Launch
PHASE 6 ¦ Post-Launch Review & Optimization
Category | Task | Description / Guidance | Due Date | Status | Owner | Reference / Link | Signature
PERFORMANCE VS. PHASE 0 METRICS
KPIs | Track KRs from Phase 0 vision statement | Measure the exact key results defined in Phase 0. Are they trending toward the 3–5 year targets? If not, identify root cause before adding features. |  | ○ Not Started |  | Ref: Phase 0 success metrics
KPIs | Marketing KPI effectiveness measured | Channel-level ROI analysis. Reallocate budget to highest-performing channels. |  | ○ Not Started
KPIs | Business case validation | Compare actual results to the business case projections from Phase 0. Are value drivers performing as assumed? Update assumptions with real data. |  | ○ Not Started
CUSTOMER FEEDBACK & MVP ITERATION
Feedback | User NPS / CSAT survey deployed | Survey early adopters within 2 weeks. Share results with product team. |  | ○ Not Started
Feedback | In-app analytics reviewed | Analyze feature adoption, session length, and drop-off. For MVP: this data drives the go/no-go decision for full product investment. |  | ○ Not Started |  | MVP: use to decide full product investment
Feedback | Testimonials & case studies initiated | Identify happy early customers. The PR/FAQ's hypothetical customer quote should now be replaced with a real one. |  | ○ Not Started |  | Replace hypothetical PR/FAQ quote with real customer
Feedback | Social sentiment & review monitoring | App store, G2, Capterra, social monitoring active. |  | ○ Not Started
ISSUE MANAGEMENT & ITERATION
Issues | Bug tracking & triage active | All reported bugs logged. Priority and owner assigned. Fix ETA published. |  | ○ Not Started
Issues | Product backlog updated | For MVP: new backlog is ordered by: (1) things blocking core user journey, (2) feedback-driven improvements, (3) features deferred from MVP scope. For full launch: standard prioritization. |  | ○ Not Started
Issues | Stakeholder post-launch update sent | Results vs. Phase 0 targets. Learnings. Next steps. |  | ○ Not Started
RETROSPECTIVE & NEXT LAUNCH
Retro | Launch retrospective conducted | What went well / what to improve / action items. Key question: did the PR/FAQ accurately predict how customers responded? |  | ○ Not Started |  | Compare PR/FAQ predictions to reality
Retro | PR/FAQ accuracy assessment | Review the original PR/FAQ against actual customer response. Did we solve the right problem? Did customers describe the value the way we predicted? Use this to improve the next PR/FAQ. |  | ○ Not Started |  | Close the Working Backwards loop
Retro | 30/60/90 day reviews scheduled | Formal reviews at 30, 60, 90 days. Agenda: KR trends, customer health, GTM optimization. |  | ○ Not Started
Retro | Next PR/FAQ or PR/FAQ iteration initiated | For MVP: based on feedback, write the next iteration's PR/FAQ before committing to full product build. Working Backwards is not a one-time exercise. |  | ○ Not Started |  | Working Backwards is continuous
David W. Lucky ¦ Senior Product Marketing Leader & Principal, CloudScale Advisory ¦ cloudscaleadvisory.com
cloudscaleadvisory.com · Strategic GTM for Cloud & AI

## Decision Log
LAUNCH DECISION LOG
# | Decision Question | Decision Made | Decision Maker | Date | Communicated To | Rationale | Revisit Date
David W. Lucky ¦ Senior Product Marketing Leader & Principal, CloudScale Advisory ¦ cloudscaleadvisory.com
cloudscaleadvisory.com · Strategic GTM for Cloud & AI